## Gantt Chart Template
Task name | Stard date | End date | Assigned | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01
Idea Collection & Competitor Logo Analysis | 2025-03-01 | 2025-03-07 | Team
Hand-drawn Logo Sketches | 2025-03-08 | 2025-03-11 | Team
Digital Logo Concepts | 2025-03-12 | 2025-03-15 | Team
Competitor Color Analysis | 2025-03-16 | 2025-03-18 | Youssef
Primary & Secondary Color Selection | 2025-03-16 | 2025-03-18 | Alaa
Font Selection & Testing | 2025-03-16 | 2025-03-18 | Hager
Brand Guidelines Preparation | 2025-03-16 | 2025-03-20 | Abdelrahman
Business Card Design | 2025-03-19 | 2025-03-21 | Youssef
Icons & Symbols Design | 2025-03-19 | 2025-03-21 | Alaa
Correct & Incorrect Logo Usage Guide | 2025-03-19 | 2025-03-20 | Hager
Letterhead Design | 2025-03-20 | 2025-03-21 | Abdelrahman
Envelope Design | 2025-03-22 | 2025-03-23 | Youssef
Mockup Design for Branding Elements | 2025-03-24 | 2025-03-27 | Team
Social Media Profile & Cover Design | 2025-03-28 | 2025-03-31 | Hager
Social Media Post Templates | 2025-03-28 | 2025-03-31 | Abdelrahman
Advertising Posters for Social Media | 2025-03-28 | 2025-03-31 | Alaa
Professional Presentation Design | 2025-03-28 | 2025-03-31 | Youssef
Company Brochure Design | 2025-04-01 | 2025-04-02 | Abdelrahman
Billboard Design | 2025-04-01 | 2025-04-02 | Alaa
Roll-up Banner Design | 2025-04-01 | 2025-04-02 | Hager
Promotional Flyer Design | 2025-04-01 | 2025-04-02 | Youssef
Promo Cards Design | 2025-04-02 | 2025-04-04 | Alaa
Website Content Preparation | 2025-04-02 | 2025-04-04 | Team
Homepage Design | 2025-04-05 | 2025-04-10 | Youssef
Service Pages Design | 2025-04-05 | 2025-04-11 | Abdelrahman
About Us & Contact Pages Design | 2025-04-12 | 2025-04-17 | Hager
Finalizing Icons & Details | 2025-04-18 | 2025-04-20 | Team
Reviewing All Designs & Ensuring Consistency | 2025-04-21 | 2025-04-23 | Team
Preparing Final Presentation | 2025-04-24 | 2025-04-28 | Team
Testing & Final Project Showcase | 2025-04-29 | 2025-05-01 | Team

## Assignees and Status
Assignees | Status
Andrew | Open
Helen | In process
Paul | Closed
Victoria | Done
Alex